## Cyclical Cleans
Name | Duration | Start Month | Finish Month | Number of Gullies
Standard Cleans | 246.84 days | April 2026 | March 2027 | 99597
North | 195.31 days | April 2026 | January 2027 | 34593
Prestbury Ward | 9.32 days | April 2026 | April 2026 | 839
Pittville Ward | 8.57 days | April 2026 | April 2026 | 771
Oakley Ward | 6.81 days | April 2026 | May 2026 | 613
Battledown Ward | 9.71 days | May 2026 | May 2026 | 874
Charlton Kings Ward | 7.62 days | May 2026 | June 2026 | 686
Charlton Park Ward | 7.04 days | June 2026 | June 2026 | 634
Leckhampton Ward | 9.71 days | June 2026 | July 2026 | 874
College Ward | 5.69 days | July 2026 | July 2026 | 512
All Saints Ward | 5.32 days | July 2026 | July 2026 | 479
St. Paul's Ward | 7.83 days | July 2026 | July 2026 | 705
St. Peter's Ward | 10.01 days | July 2026 | July 2026 | 901
Lansdown Ward | 5.47 days | July 2026 | August 2026 | 492
Park Ward | 9.69 days | August 2026 | August 2026 | 872
Warden Hill Ward | 11.26 days | August 2026 | September 2026 | 1013
Up Hatherley Ward | 12.92 days | September 2026 | September 2026 | 1163
Badgeworth Ward | 0.09 days | September 2026 | September 2026 | 8
Benhall and the Reddings Ward | 13.8 days | September 2026 | October 2026 | 1242
St. Mark's Ward | 8.72 days | October 2026 | October 2026 | 785
Hesters Way Ward | 12.68 days | October 2026 | November 2026 | 1141
Springbank Ward | 13.74 days | November 2026 | December 2026 | 1237
Swindon Village Ward | 13.04 days | December 2026 | December 2026 | 1174
Bishop's Cleeve | 29.54 days | April 2026 | May 2026 | 2659
Minsterworth | 0.48 days | May 2026 | May 2026 | 43
Highnam | 5.29 days | May 2026 | May 2026 | 476
Maisemore | 0.73 days | May 2026 | May 2026 | 66
Longford | 3.23 days | May 2026 | May 2026 | 291
Sandhurst | 0.99 days | May 2026 | May 2026 | 89
Twigworth | 0.04 days | May 2026 | May 2026 | 4
Innsworth | 5.08 days | May 2026 | June 2026 | 457
Down Hatherley | 0.99 days | June 2026 | June 2026 | 89
Churchdown | 19.22 days | June 2026 | July 2026 | 1730
Hucclecote | 7.3 days | July 2026 | July 2026 | 659
Brockworth | 14.33 days | July 2026 | July 2026 | 1290
Great Witcombe | 0.38 days | July 2026 | July 2026 | 34
Badgeworth | 5.14 days | July 2026 | August 2026 | 463
Shurdington | 3.6 days | August 2026 | August 2026 | 324
Staverton | 0.76 days | August 2026 | August 2026 | 68
Boddington | 0.91 days | August 2026 | August 2026 | 82
Uckington | 1.7 days | August 2026 | August 2026 | 153
Elmstone Hardwicke | 0.41 days | August 2026 | August 2026 | 37
Leigh | 0.21 days | August 2026 | August 2026 | 19
Norton | 1.57 days | August 2026 | August 2026 | 141
Hasfield | 0.49 days | August 2026 | August 2026 | 44
Ashleworth | 1.76 days | August 2026 | August 2026 | 162
Tirley | 1.28 days | August 2026 | August 2026 | 115
Deerhurst | 1.43 days | August 2026 | August 2026 | 129
Chaceley | 0.21 days | August 2026 | August 2026 | 19
Forthampton | 0.18 days | August 2026 | August 2026 | 16
Tewkesbury | 24.59 days | August 2026 | October 2026 | 2213
Twyning | 3.73 days | October 2026 | October 2026 | 336
Wheatpieces | 9.76 days | October 2026 | October 2026 | 878
Northway | 11.63 days | October 2026 | November 2026 | 1047
Ashchurch Rural | 2.22 days | November 2026 | November 2026 | 200
Stoke Orchard | 3.57 days | November 2026 | November 2026 | 321
Gotherington | 2.89 days | November 2026 | November 2026 | 260
Prescott | 0.27 days | November 2026 | November 2026 | 24
Gretton | 1.47 days | November 2026 | November 2026 | 132
Alderton | 1.49 days | November 2026 | November 2026 | 134
Oxenton | 0.32 days | November 2026 | November 2026 | 29
Teddington | 0.91 days | November 2026 | November 2026 | 82
Dumbleton | 1.12 days | November 2026 | November 2026 | 101
Toddington | 0.78 days | November 2026 | November 2026 | 70
Stanton | 0.42 days | November 2026 | November 2026 | 38
Buckland | 0.48 days | November 2026 | November 2026 | 43
Snowshill | 0.42 days | November 2026 | November 2026 | 38
Stanway | 0.79 days | November 2026 | December 2026 | 71
Winchcombe | 9.83 days | December 2026 | December 2026 | 885
Sudeley | 0.57 days | December 2026 | December 2026 | 51
Hawling | 0.11 days | December 2026 | December 2026 | 10
Southam | 2.9 days | December 2026 | December 2026 | 261
Woodmancote | 7.79 days | December 2026 | December 2026 | 701
West | 152.95 days | April 2026 | October 2026 | 13767
Tidenham | 9.31 days | April 2026 | April 2026 | 838
Hewelsfield and Brockweir | 0.62 days | April 2026 | April 2026 | 56
Woolaston | 2.69 days | April 2026 | April 2026 | 242
Alvington | 1 day | April 2026 | April 2026 | 90
Aylburton | 1.39 days | April 2026 | April 2026 | 125
St. Briavels | 2.99 days | April 2026 | April 2026 | 269
Newland | 2.41 days | April 2026 | April 2026 | 217
Coleford | 15.36 days | April 2026 | May 2026 | 1382
Staunton Coleford | 0.66 days | May 2026 | May 2026 | 59
English Bicknor | 1.24 days | May 2026 | May 2026 | 112
Lydbrook | 3.21 days | May 2026 | May 2026 | 289
Ruardean | 3.24 days | May 2026 | June 2026 | 292
Drybrook | 5.19 days | June 2026 | June 2026 | 467
Cinderford | 15.89 days | June 2026 | July 2026 | 1430
Ruspidge and Soudley | 5.84 days | July 2026 | July 2026 | 526
West Dean | 18.3 days | July 2026 | August 2026 | 1646
Lydney | 18.52 days | August 2026 | August 2026 | 1667
Awre | 4.74 days | August 2026 | August 2026 | 427
Newnham | 2.2 days | August 2026 | September 2026 | 198
Littledean | 1.93 days | September 2026 | September 2026 | 174
Westbury-on-Severn | 2.69 days | September 2026 | September 2026 | 242
Blaisdon | 1.03 days | September 2026 | September 2026 | 93
Mitcheldean | 3.86 days | September 2026 | September 2026 | 347
Longhope | 3.2 days | September 2026 | September 2026 | 288
Huntley | 1.96 days | September 2026 | September 2026 | 176
Churcham | 0.81 days | September 2026 | September 2026 | 73
Tibberton | 1.1 days | September 2026 | October 2026 | 98
Taynton | 0.63 days | October 2026 | October 2026 | 57
Newent | 12.18 days | October 2026 | October 2026 | 1096
Gorsley and Kilcot | 0.22 days | October 2026 | October 2026 | 20
Oxenhall | 0.24 days | October 2026 | October 2026 | 22
Kempley | 0.26 days | October 2026 | October 2026 | 23
Dymock | 1.62 days | October 2026 | October 2026 | 146
Bromesberrow | 0.52 days | October 2026 | October 2026 | 47
Redmarley D'abitot | 1.03 days | October 2026 | October 2026 | 93
Pauntley | 0.31 days | October 2026 | October 2026 | 28
Upleadon | 0.4 days | October 2026 | October 2026 | 36
Staunton | 1.77 days | October 2026 | October 2026 | 159
Corse | 0.7 days | October 2026 | October 2026 | 63
Hartpury | 1.39 days | October 2026 | October 2026 | 125
Rudford and Highleadon | 0.3 days | October 2026 | October 2026 | 27
South | 246.84 days | April 2026 | March 2027 | 39750
Quedgeley Fieldcourt Ward | 37.6 days | April 2026 | May 2026 | 3384
Quedgeley Severn Vale Ward | 19.97 days | May 2026 | June 2026 | 1797
Grange Ward | 11.94 days | June 2026 | July 2026 | 1075
Tuffley Ward | 10.26 days | July 2026 | July 2026 | 923
Matson and Robinswood Ward | 17.53 days | July 2026 | August 2026 | 1578
Moreland Ward | 9.98 days | August 2026 | August 2026 | 898
Podsmead Ward | 8.92 days | August 2026 | September 2026 | 803
Westgate Ward | 17.99 days | September 2026 | October 2026 | 1619
Barton and Tredworth Ward | 11.4 days | October 2026 | October 2026 | 1026
Abbey Ward | 18.61 days | October 2026 | November 2026 | 1748
Hucclecote Ward | 18.76 days | November 2026 | December 2026 | 1688
Barnwood Ward | 26.06 days | December 2026 | January 2027 | 2345
Elmbridge Ward | 8.27 days | January 2027 | January 2027 | 744
Longlevens Ward | 20.08 days | January 2027 | February 2027 | 1807
Kingsholm and Wotton Ward | 9.47 days | February 2027 | March 2027 | 852
Whitminster | 2.68 days | April 2026 | April 2026 | 241
Moreton Valence | 0.5 days | April 2026 | April 2026 | 45
Standish | 0.61 days | April 2026 | April 2026 | 55
Haresfield | 2.17 days | April 2026 | April 2026 | 195
Hardwicke | 13.67 days | April 2026 | April 2026 | 1230
Elmore | 0.59 days | April 2026 | April 2026 | 53
Longney and Epney | 0.67 days | April 2026 | April 2026 | 60
Fretherne with Saul | 0.8 days | April 2026 | April 2026 | 72
Arlingham | 1.26 days | April 2026 | May 2026 | 113
Frampton on Severn | 2.03 days | May 2026 | May 2026 | 183
Slimbridge | 2.91 days | May 2026 | May 2026 | 262
Coaley | 1.89 days | May 2026 | May 2026 | 170
Cam | 14.61 days | May 2026 | June 2026 | 1315
Stinchcombe | 0.78 days | June 2026 | June 2026 | 70
Hamfallow | 1.9 days | June 2026 | June 2026 | 171
Hinton | 1.99 days | June 2026 | June 2026 | 179
Berkeley | 3.87 days | June 2026 | June 2026 | 348
Ham and Stone | 1.77 days | June 2026 | June 2026 | 159
Alkington | 1.26 days | June 2026 | June 2026 | 162
North Nibley | 1.11 days | June 2026 | June 2026 | 100
Dursley | 11.36 days | June 2026 | July 2026 | 1022
Uley | 1.47 days | July 2026 | July 2026 | 132
Owlpen | 0.04 days | July 2026 | July 2026 | 4
Wotton-under-Edge | 6.67 days | July 2026 | July 2026 | 600
Kingswood | 2.53 days | July 2026 | July 2026 | 228
Hillesley and Tresham | 0.94 days | July 2026 | July 2026 | 85
Alderley | 0.36 days | July 2026 | July 2026 | 32
Horsley | 0.67 days | July 2026 | July 2026 | 60
Nympsfield | 0.62 days | July 2026 | July 2026 | 56
Frocester | 0.59 days | July 2026 | July 2026 | 53
Leonard Stanley | 3.69 days | July 2026 | July 2026 | 332
King's Stanley | 3.99 days | July 2026 | August 2026 | 359
Woodchester | 1.98 days | August 2026 | August 2026 | 178
Nailsworth | 8.1 days | August 2026 | August 2026 | 729
Minchinhampton | 8.39 days | August 2026 | August 2026 | 755
Rodborough | 6.07 days | August 2026 | September 2026 | 546
Brimscombe and Thrupp | 2.13 days | September 2026 | September 2026 | 192
Chalford | 10.6 days | September 2026 | September 2026 | 954
Bisley-with-Lypiatt | 3.73 days | September 2026 | September 2026 | 336
Stroud | 17.83 days | October 2026 | October 2026 | 1605
Cainscross | 9.64 days | October 2026 | November 2026 | 868
Stonehouse | 14.57 days | November 2026 | November 2026 | 1311
Eastington | 5.29 days | November 2026 | December 2026 | 476
Randwick | 2.19 days | December 2026 | December 2026 | 197
Whiteshill and Ruscombe | 1.23 days | December 2026 | December 2026 | 111
Pitchcombe | 0.27 days | December 2026 | December 2026 | 24
Harescombe | 0.73 days | December 2026 | December 2026 | 68
Painswick | 3.44 days | December 2026 | December 2026 | 310
Miserden | 0.4 days | December 2026 | December 2026 | 36
Cranham | 0.48 days | December 2026 | December 2026 | 43
Upton St. Leonards | 5.26 days | December 2026 | December 2026 | 473
Brookthorpe-with-Whaddon | 0.91 days | December 2026 | December 2026 | 82
East | 172.85 days | April 2026 | November 2026 | 15554
Ebrington | 1.22 days | April 2026 | April 2026 | 110
Mickleton | 3.93 days | April 2026 | April 2026 | 354
Weston Subedge | 1.02 days | April 2026 | April 2026 | 92
Aston Subedge | 0.17 days | April 2026 | April 2026 | 15
Saintbury | 0.1 days | April 2026 | April 2026 | 9
Willersey | 1.93 days | April 2026 | April 2026 | 174
Chipping Campden | 4.3 days | April 2026 | April 2026 | 387
Blockley | 3.17 days | April 2026 | April 2026 | 285
Batsford | 0.47 days | April 2026 | April 2026 | 42
Todenham | 0.52 days | April 2026 | April 2026 | 47
Moreton-in-Marsh | 9.11 days | April 2026 | May 2026 | 820
Bourton-on-the-Hill | 0.18 days | May 2026 | May 2026 | 16
Cutsdean | 0.01 days | May 2026 | May 2026 | 1
Temple Guiting | 0.49 days | May 2026 | May 2026 | 44
Swell | 0.37 days | May 2026 | May 2026 | 33
Condicote | 0.14 days | May 2026 | May 2026 | 13
Longborough | 0.8 days | May 2026 | May 2026 | 72
Donnington | 0.07 days | May 2026 | May 2026 | 6
Evenlode | 0.24 days | May 2026 | May 2026 | 22
Adlestrop | 0.22 days | May 2026 | May 2026 | 20
Oddington | 0.66 days | May 2026 | May 2026 | 59
Bledington | 0.64 days | May 2026 | May 2026 | 58
Maugersbury | 0.27 days | May 2026 | May 2026 | 24
Broadwell | 0.67 days | May 2026 | May 2026 | 60
Stow-on-the-Wold | 2.69 days | May 2026 | May 2026 | 242
Upper Slaughter | 0.3 days | May 2026 | May 2026 | 27
Naunton | 0.48 days | May 2026 | May 2026 | 43
Guiting Power | 0.43 days | May 2026 | May 2026 | 39
Sevenhampton | 0.21 days | May 2026 | May 2026 | 19
Whittington | 0.31 days | May 2026 | May 2026 | 28
Andoversford | 2.01 days | May 2026 | May 2026 | 181
Shipton | 0.32 days | May 2026 | May 2026 | 29
Compton Abdale | 0.4 days | May 2026 | May 2026 | 36
Hazleton | 0.29 days | May 2026 | May 2026 | 26
Turkdean | 0.06 days | May 2026 | May 2026 | 5
Notgrove | 0.08 days | May 2026 | May 2026 | 7
Cold Aston | 0.33 days | May 2026 | May 2026 | 30
Bourton-on-the-Water | 10.36 days | May 2026 | June 2026 | 932
Lower Slaughter | 0.67 days | June 2026 | June 2026 | 60
Wick Rissington | 0.38 days | June 2026 | June 2026 | 34
Icomb | 0.28 days | June 2026 | June 2026 | 25
Westcote | 0.29 days | June 2026 | June 2026 | 26
Upper Rissington | 2.37 days | June 2026 | June 2026 | 213
Little Rissington | 1.13 days | June 2026 | June 2026 | 102
Clapton | 0.22 days | June 2026 | June 2026 | 20
Farmington | 0.48 days | June 2026 | June 2026 | 43
Sherborne | 0.57 days | June 2026 | June 2026 | 51
Great Rissington | 0.64 days | June 2026 | June 2026 | 58
Barrington | 0.62 days | June 2026 | June 2026 | 56
Windrush | 0.14 days | June 2026 | June 2026 | 13
Aldsworth | 0.29 days | June 2026 | June 2026 | 26
Northleach with Eastington | 4.32 days | June 2026 | June 2026 | 389
Hampnett | 0.21 days | June 2026 | June 2026 | 19
Yanworth | 0.1 days | June 2026 | June 2026 | 9
Chedworth | 1.06 days | June 2026 | June 2026 | 95
Withington | 1.02 days | June 2026 | June 2026 | 92
Colesbourne | 0.09 days | June 2026 | June 2026 | 8
Dowdeswell | 0.42 days | June 2026 | June 2026 | 38
Coberley | 0.72 days | June 2026 | June 2026 | 65
Cowley | 1.28 days | June 2026 | July 2026 | 115
Brimpsfield | 0.3 days | July 2026 | July 2026 | 27
Syde | 0.57 days | July 2026 | July 2026 | 51
Elkstone | 0.66 days | July 2026 | July 2026 | 59
Rendcomb | 0.54 days | July 2026 | July 2026 | 49
North Cerney | 0.76 days | July 2026 | July 2026 | 68
Coln St. Dennis | 0.38 days | July 2026 | July 2026 | 34
Winson | 0.16 days | July 2026 | July 2026 | 14
Bibury | 0.8 days | July 2026 | July 2026 | 72
Coln St. Aldwyns | 0.39 days | July 2026 | July 2026 | 35
Eastleach | 0.27 days | July 2026 | July 2026 | 24
Hatherop | 0.38 days | July 2026 | July 2026 | 34
Southrop | 0.73 days | July 2026 | July 2026 | 66
Lechlade | 5.3 days | July 2026 | July 2026 | 477
Kempsford | 4.54 days | July 2026 | July 2026 | 409
Fairford | 7.43 days | July 2026 | August 2026 | 669
Quenington | 0.71 days | August 2026 | August 2026 | 64
Maiseyhampton | 0.88 days | August 2026 | August 2026 | 79
Poulton | 0.76 days | August 2026 | August 2026 | 68
Down Ampney | 1.54 days | August 2026 | August 2026 | 139
Ampney St. Peter | 0.08 days | August 2026 | August 2026 | 7
Ampney St. Mary | 0.38 days | August 2026 | August 2026 | 34
Ampney Crucis | 1.61 days | August 2026 | August 2026 | 145
Barnsley | 0.02 days | August 2026 | August 2026 | 2
Preston | 2.96 days | August 2026 | August 2026 | 266
Driffield | 0.99 days | August 2026 | August 2026 | 89
South Cerney | 8.84 days | August 2026 | August 2026 | 796
Siddington | 3.33 days | August 2026 | September 2026 | 300
Cirencester | 38.07 days | September 2026 | October 2026 | 3426
Baunton | 0.6 days | October 2026 | October 2026 | 54
Bagendon | 0.56 days | October 2026 | October 2026 | 50
Daglingworth | 0.8 days | October 2026 | October 2026 | 72
Duntisbourne Rouse | 0.23 days | October 2026 | October 2026 | 21
Duntisbourne Abbots | 1.31 days | October 2026 | November 2026 | 118
Winstone | 0.77 days | November 2026 | November 2026 | 69
Edgeworth | 0.2 days | November 2026 | November 2026 | 18
Sapperton | 0.91 days | November 2026 | November 2026 | 82
Coates | 0.58 days | November 2026 | November 2026 | 52
Kemble | 1.82 days | November 2026 | November 2026 | 164
Somerford Keynes | 1.11 days | November 2026 | November 2026 | 100
Poole Keynes | 0.66 days | November 2026 | November 2026 | 59
Rodmarton | 0.43 days | November 2026 | November 2026 | 39
Cherington | 0.12 days | November 2026 | November 2026 | 11
Ashley | 0.27 days | November 2026 | November 2026 | 24
Long Newnton | 0.07 days | November 2026 | November 2026 | 6
Shipton Moyne | 0.4 days | November 2026 | November 2026 | 36
Tetbury Upton | 0.61 days | November 2026 | November 2026 | 55
Tetbury | 8.47 days | November 2026 | November 2026 | 762
Avening | 1.38 days | November 2026 | November 2026 | 124
Beverston | 0.16 days | November 2026 | November 2026 | 14
Kingscote | 0.43 days | November 2026 | November 2026 | 39
Ozleworth | 0.07 days | November 2026 | November 2026 | 6
Boxwell with Leighterton | 0.32 days | November 2026 | November 2026 | 29
Westonbirt with Lasborough | 0.54 days | November 2026 | November 2026 | 49
Didmarton | 0.38 days | November 2026 | November 2026 | 34

## A&B Roads
Name | Duration | Number of Gullies | Start Month | Finish Month
A&B Roads | 215.62 days | 25762 | April 2026 | January 2027
North | 76.53 days | 6886 | October 2026 | January 2027
A38 | 15.18 days | 1366 | October 2026 | October 2026
A40 | 6.07 days | 546 | October 2026 | October 2026
A4013 | 1.51 days | 136 | October 2026 | October 2026
A4015 | 0.19 days | 17 | October 2026 | November 2026
A4019 | 6.39 days | 575 | November 2026 | November 2026
A417 | 2.69 days | 242 | November 2026 | November 2026
A435 | 8.01 days | 721 | November 2026 | November 2026
A436 | 0.62 days | 56 | November 2026 | November 2026
A438 | 1.8 days | 162 | November 2026 | November 2026
A46 | 9.17 days | 825 | November 2026 | November 2026
A48 | 2.86 days | 257 | November 2026 | December 2026
B4063 | 3.14 days | 283 | December 2026 | December 2026
B4068 | 0.28 days | 25 | December 2026 | December 2026
B4075 | 2.06 days | 185 | December 2026 | December 2026
B4077 | 1.86 days | 167 | December 2026 | December 2026
B4078 | 1.49 days | 134 | December 2026 | December 2026
B4079 | 0.59 days | 53 | December 2026 | December 2026
B4080 | 0.43 days | 39 | December 2026 | December 2026
B4213 | 1.67 days | 150 | December 2026 | December 2026
B4215 | 0.6 days | 54 | December 2026 | January 2027
B4632 | 6.6 days | 594 | January 2027 | January 2027
B4633 | 0.71 days | 64 | January 2027 | January 2027
B4634 | 1.73 days | 156 | January 2027 | January 2027
B4641 | 0.88 days | 79 | January 2027 | January 2027
West | 60.87 days | 5482 | April 2026 | June 2026
A4136 | 6.73 days | 606 | April 2026 | April 2026
A40 | 0.02 days | 2 | April 2026 | April 2026
A4151 | 2.94 days | 265 | April 2026 | April 2026
A417 | 2.51 days | 226 | April 2026 | April 2026
A4172 | 0.33 days | 30 | April 2026 | April 2026
A466 | 2.41 days | 217 | April 2026 | April 2026
A48 | 17.94 days | 1615 | April 2026 | April 2026
B4024 | 0.01 days | 1 | April 2026 | May 2026
B4028 | 0.63 days | 57 | May 2026 | May 2026
B4208 | 0.16 days | 14 | May 2026 | May 2026
B4211 | 0.04 days | 4 | May 2026 | May 2026
B4213 | 0.12 days | 11 | May 2026 | May 2026
A449 | 0.01 days | 1 | May 2026 | May 2026
B4215 | 5.46 days | 491 | May 2026 | May 2026
B4216 | 1.77 days | 159 | May 2026 | May 2026
B4221 | 0.9 days | 81 | May 2026 | May 2026
B4222 | 0.01 days | 1 | May 2026 | May 2026
B4224 | 0.78 days | 70 | May 2026 | May 2026
B4226 | 2.09 days | 188 | May 2026 | May 2026
B4227 | 2.28 days | 205 | May 2026 | June 2026
B4228 | 5.18 days | 466 | June 2026 | June 2026
B4231 | 2.73 days | 246 | June 2026 | June 2026
B4234 | 5.27 days | 474 | June 2026 | June 2026
B4432 | 0.58 days | 52 | June 2026 | June 2026
South | 84.62 days | 7615 | October 2026 | January 2027
A38 | 18.68 days | 1681 | October 2026 | October 2026
A40 | 0.71 days | 64 | October 2026 | October 2026
A4135 | 3 days | 270 | October 2026 | October 2026
A417 | 3.77 days | 339 | October 2026 | November 2026
A4171 | 1.32 days | 119 | November 2026 | November 2026
A4173 | 3.47 days | 312 | November 2026 | November 2026
A419 | 10.79 days | 971 | November 2026 | November 2026
A430 | 4.97 days | 447 | November 2026 | November 2026
A4301 | 1.03 days | 93 | November 2026 | December 2026
A4302 | 0.98 days | 88 | December 2026 | December 2026
A46 | 8.37 days | 753 | December 2026 | December 2026
B4008 | 8.36 days | 752 | December 2026 | December 2026
B4014 | 0.57 days | 51 | December 2026 | December 2026
B4058 | 2.17 days | 195 | December 2026 | January 2027
B4060 | 1.51 days | 136 | January 2027 | January 2027
B4062 | 0.54 days | 49 | January 2027 | January 2027
B4063 | 2.34 days | 211 | January 2027 | January 2027
B4066 | 4.29 days | 386 | January 2027 | January 2027
B4070 | 1.01 days | 91 | January 2027 | January 2027
B4071 | 1.44 days | 130 | January 2027 | January 2027
B4072 | 2.13 days | 192 | January 2027 | January 2027
B4073 | 3.17 days | 285 | January 2027 | January 2027
East | 64.2 days | 5779 | April 2026 | June 2026
A361 | 1.71 days | 154 | April 2026 | April 2026
A40 | 11.31 days | 1018 | April 2026 | April 2026
A4135 | 0.62 days | 56 | April 2026 | April 2026
A417 | 6.33 days | 570 | April 2026 | April 2026
A419 | 4.17 days | 375 | April 2026 | April 2026
A424 | 0.72 days | 65 | April 2026 | May 2026
A429 | 12.08 days | 1087 | May 2026 | May 2026
A433 | 3.86 days | 347 | May 2026 | May 2026
A435 | 5.01 days | 451 | May 2026 | May 2026
A436 | 1.73 days | 156 | May 2026 | June 2026
A44 | 2.24 days | 202 | June 2026 | June 2026
A46 | 1.68 days | 151 | June 2026 | June 2026
B4014 | 1.87 days | 168 | June 2026 | June 2026
B4035 | 1.08 days | 97 | June 2026 | June 2026
B4058 | 0.07 days | 6 | June 2026 | June 2026
B4068 | 0.83 days | 75 | June 2026 | June 2026
B4070 | 0.63 days | 57 | June 2026 | June 2026
B4077 | 0.63 days | 57 | June 2026 | June 2026
B4081 | 1.14 days | 103 | June 2026 | June 2026
B4425 | 2.42 days | 218 | April 2026 | April 2026
B4450 | 0.43 days | 39 | April 2026 | April 2026
B4479 | 1.18 days | 106 | April 2026 | April 2026
B4632 | 2.29 days | 206 | April 2026 | April 2026
B4696 | 0.17 days | 15 | April 2026 | April 2026

## Multicleans
Name | Duration | Start Month | Finish Month | Number of Gullies
Multicleans | 20.17 days |  |  | 4318
North | 8.13 days | April 2026 | Apr-26 | 769
Badgeworth | 0.21 days | April 2026 | April 2026 | 19
Cheltenham non-parish | 0.29 days | April 2026 | April 2026 | 14
Charlton Kings | 0.16 days | April 2026 | April 2026 | 14
Boddington | 0.3 days | April 2026 | April 2026 | 27
Churchdown | 0.28 days | April 2026 | April 2026 | 24
Twigworth | 0.04 days | April 2026 | April 2026 | 2
Longford | 0.34 days | April 2026 | April 2026 | 79
Maisemore | 0.01 days | April 2026 | April 2026 | 1
Sandhurst | 0.45 days | April 2026 | April 2026 | 41
Ashleworth | 0.39 days | April 2026 | April 2026 | 22
Norton | 0.08 days | April 2026 | April 2026 | 7
Deerhurst | 0.01 days | April 2026 | April 2026 | 1
Chaceley | 0.16 days | April 2026 | April 2026 | 14
Tewkesbury | 0.63 days | April 2026 | April 2026 | 57
Twyning | 0.68 days | April 2026 | April 2026 | 62
Ashchurch Rural | 0.62 days | April 2026 | April 2026 | 56
Teddington | 0.09 days | April 2026 | April 2026 | 8
Bishop's Cleeve | 2.16 days | April 2026 | April 2026 | 204
Southam | 0.24 days | April 2026 | April 2026 | 22
Sudeley | 0.15 days | April 2026 | April 2026 | 14
Winchcombe | 0.55 days | April 2026 | April 2026 | 50
Gretton | 0.29 days | April 2026 | April 2026 | 31
West | 7.69 days | April 2026 | Apr-26 | 764
Bromesberrow | 0.08 days | April 2026 | April 2026 | 7
Redmarley d'Abitot | 0.16 days | April 2026 | April 2026 | 15
Newent | 0.24 days | April 2026 | April 2026 | 22
Oxenhall | 0.17 days | April 2026 | April 2026 | 16
Rudford and Highleadon | 0.2 days | April 2026 | April 2026 | 18
Tibberton | 0.02 days | April 2026 | April 2026 | 2
Churcham | 0.01 days | April 2026 | April 2026 | 1
Westbury-on-Severn | 0.65 days | April 2026 | April 2026 | 59
Blaisdon | 0.38 days | April 2026 | April 2026 | 35
Newnham | 0.31 days | April 2026 | April 2026 | 28
Ruspidge and Soudley | 0.28 days | April 2026 | April 2026 | 25
Littledean | 0.58 days | April 2026 | April 2026 | 53
Cinderford | 0.54 days | April 2026 | April 2026 | 117
Longhope | 0.72 days | April 2026 | April 2026 | 66
Drybrook | 0.34 days | April 2026 | April 2026 | 26
Lydbrook | 0.03 days | April 2026 | April 2026 | 3
English Bicknor | 0.02 days | April 2026 | April 2026 | 2
Coleford | 0.51 days | April 2026 | April 2026 | 48
Newland | 0.41 days | April 2026 | April 2026 | 37
West Dean | 0.51 days | April 2026 | April 2026 | 46
Awre | 0.22 days | April 2026 | April 2026 | 20
Lydney | 1.1 days | April 2026 | April 2026 | 99
Alvington | 0.21 days | April 2026 | April 2026 | 19
South | 10.68 days | April 2026 | Apr-26 | 971
Whitminster | 0.01 days | April 2026 | April 2026 | 1
Moreton Valence | 0.1 days | April 2026 | April 2026 | 9
Elmore | 0.03 days | April 2026 | April 2026 | 3
Longney and Epney | 0.3 days | April 2026 | April 2026 | 27
Fretherne with Saul | 0.48 days | April 2026 | April 2026 | 56
Arlingham | 0.23 days | April 2026 | April 2026 | 22
Frampton on Severn | 0.52 days | April 2026 | April 2026 | 47
Slimbridge | 0.93 days | April 2026 | April 2026 | 83
Hamfallow | 0.08 days | April 2026 | April 2026 | 7
Berkeley | 0.12 days | April 2026 | April 2026 | 11
Ham and Stone | 0.08 days | April 2026 | April 2026 | 7
Alkington | 0.17 days | April 2026 | April 2026 | 15
Cam | 0.37 days | April 2026 | April 2026 | 37
Dursley | 0.08 days | April 2026 | April 2026 | 7
Uley | 0.12 days | April 2026 | April 2026 | 11
Wotton-under-Edge | 0.31 days | April 2026 | April 2026 | 28
Nailsworth | 0.96 days | April 2026 | April 2026 | 87
Minchinhampton | 0.08 days | April 2026 | April 2026 | 7
Woodchester | 0.24 days | April 2026 | April 2026 | 22
Rodborough | 0.14 days | April 2026 | April 2026 | 13
Brimscombe and Thrupp | 0.59 days | April 2026 | April 2026 | 53
Chalford | 0.69 days | April 2026 | April 2026 | 68
Bisley-with-Lypiatt | 0.4 days | April 2026 | April 2026 | 36
Cranham | 0.49 days | April 2026 | April 2026 | 29
Upton St. Leonards | 0.45 days | April 2026 | April 2026 | 41
Painswick | 0.27 days | April 2026 | April 2026 | 24
Stroud | 0.41 days | April 2026 | April 2026 | 37
Cainscross | 0.19 days | April 2026 | April 2026 | 17
King's Stanley | 0.12 days | April 2026 | April 2026 | 11
Leonard Stanley | 0.57 days | April 2026 | April 2026 | 53
Stonehouse | 0.86 days | April 2026 | April 2026 | 78
Haresfield | 0.29 days | April 2026 | April 2026 | 24
East | 20.17 days | April 2026 | April 20263 | 1814
Weston Subedge | 0.31 days | April 2026 | April 2026 | 28
Coberley | 0.02 days | April 2026 | April 2026 | 2
Cowley | 0.01 days | April 2026 | April 2026 | 1
Chipping Campden | 0.52 days | April 2026 | April 2026 | 17
Blockley | 0.11 days | April 2026 | April 2026 | 10
Moreton-in-Marsh | 0.39 days | April 2026 | April 2026 | 35
Evenlode | 0.01 days | April 2026 | April 2026 | 1
Condicote | 0.01 days | April 2026 | April 2026 | 1
Swell | 0.03 days | April 2026 | April 2026 | 3
Bledington | 0.08 days | April 2026 | April 2026 | 3
Lower Slaughter | 0.34 days | April 2026 | April 2026 | 34
Upper Slaughter | 0.08 days | April 2026 | April 2026 | 7
Naunton | 0.24 days | April 2026 | April 2026 | 22
Whittington | 0.1 days | April 2026 | April 2026 | 9
Andoversford | 0.72 days | April 2026 | April 2026 | 100
Chedworth | 0.21 days | April 2026 | April 2026 | 19
Coln St. Dennis | 0.13 days | April 2026 | April 2026 | 12
Barrington | 0.72 days | April 2026 | April 2026 | 65
Windrush | 0.68 days | April 2026 | April 2026 | 62
Sherborne | 1.2 days | April 2026 | April 2026 | 108
Farmington | 0.72 days | April 2026 | April 2026 | 65
Northleach with Eastington | 1 day | April 2026 | April 2026 | 91
Hampnett | 2.03 days | April 2026 | April 2026 | 183
Hazleton | 0.44 days | April 2026 | April 2026 | 40
Compton Abdale | 0.37 days | April 2026 | April 2026 | 34
Shipton | 1.71 days | April 2026 | April 2026 | 154
Dowdeswell | 0.65 days | April 2026 | April 2026 | 59
Elkstone | 0.4 days | April 2026 | April 2026 | 36
Syde | 0.41 days | April 2026 | April 2026 | 37
Colesbourne | 0.09 days | April 2026 | April 2026 | 8
Daglingworth | 0.02 days | April 2026 | April 2026 | 2
Cirencester | 3.1 days | April 2026 | April 2026 | 264
Siddington | 0.2 days | April 2026 | April 2026 | 18
Ampney St. Mary | 0.1 days | April 2026 | April 2026 | 12
Bibury | 0.1 days | April 2026 | April 2026 | 9
Fairford | 0.04 days | April 2026 | April 2026 | 4
South Cerney | 1.71 days | April 2026 | April 2026 | 154
Somerford Keynes | 0.02 days | April 2026 | April 2026 | 2
Avening | 0.04 days | April 2026 | April 2026 | 4
Tetbury Upton | 0.03 days | April 2026 | April 2026 | 3
Tetbury | 0.57 days | April 2026 | April 2026 | 51
Long Newnton | 0.03 days | April 2026 | April 2026 | 3
Shipton Moyne | 0.3 days | April 2026 | April 2026 | 27
Westonbirt with Lasborough | 0.18 days | April 2026 | April 2026 | 15

## Small Unit
Name | Duration | Start Month | Finish Month | Number of Gullies
Small Units | 132.57 days |  |  | 3326
West | 46.8 days | April 2026 | June 2026 | 1233
Tidenham | 1.36 days | April 2026 | April 2026 | 34
Woolaston | 1.92 days | April 2026 | April 2026 | 48
Hewelsfield and Brockweir | 1.36 days | April 2026 | April 2026 | 34
St. Briavels | 3.8 days | April 2026 | April 2026 | 95
Alvington | 0.24 days | April 2026 | April 2026 | 6
Aylburton | 0.56 days | April 2026 | April 2026 | 14
Lydney | 0.48 days | April 2026 | April 2026 | 12
Awre | 7.2 days | April 2026 | April 2026 | 180
West Dean | 4.76 days | April 2026 | April 2026 | 119
Newland | 0.4 days | April 2026 | May 2026 | 10
Coleford | 1.12 days | May 2026 | May 2026 | 28
Staunton Coleford | 0.8 days | May 2026 | May 2026 | 20
English Bicknor | 0.52 days | May 2026 | May 2026 | 13
Lydbrook | 3.96 days | May 2026 | May 2026 | 99
Ruardean | 0.88 days | May 2026 | May 2026 | 22
Drybrook | 1.16 days | May 2026 | May 2026 | 29
Cinderford | 2.2 days | May 2026 | May 2026 | 55
Ruspidge and Soudley | 1.84 days | May 2026 | May 2026 | 46
Newnham | 4 days | May 2026 | May 2026 | 100
Littledean | 1.64 days | May 2026 | May 2026 | 41
Mitcheldean | 1.08 days | May 2026 | May 2026 | 27
Longhope | 2.68 days | May 2026 | June 2026 | 67
Blaisdon | 0.72 days | June 2026 | June 2026 | 18
Westbury-on-Severn | 1.6 days | June 2026 | June 2026 | 40
Taynton | 0.64 days | June 2026 | June 2026 | 16
Newent | 1.36 days | June 2026 | June 2026 | 34
Gorsley and Kilcot | 0.04 days | June 2026 | June 2026 | 1
Oxenhall | 0.04 days | June 2026 | June 2026 | 1
Dymock | 0.04 days | June 2026 | June 2026 | 1
Pauntley | 0.12 days | June 2026 | June 2026 | 3
Redmarley D'Abitot | 0.28 days | June 2026 | June 2026 | 7
Bromesberrow | 0.52 days | June 2026 | June 2026 | 13
North | 83.33 days | June 2026 | June 20262 | 297
Maisemore | 0.04 days | June 2026 | June 2026 | 1
Leigh | 0.4 days | June 2026 | June 2026 | 10
Deerhurst | 0.16 days | June 2026 | June 2026 | 4
Tewkesbury | 0.84 days | June 2026 | June 2026 | 21
Twyning | 0.64 days | June 2026 | June 2026 | 16
Ashchurch Rural | 0.16 days | June 2026 | June 2026 | 4
Stanton | 0.16 days | June 2026 | June 2026 | 4
Toddington | 0.2 days | June 2026 | June 2026 | 5
Gretton | 0.24 days | June 2026 | June 2026 | 6
Prescott | 0.2 days | June 2026 | June 2026 | 5
Winchcombe | 1.04 days | June 2026 | June 2026 | 26
Hawling | 0.08 days | June 2026 | June 2026 | 2
Southam | 0.32 days | June 2026 | June 2026 | 8
Woodmancote | 1.88 days | June 2026 | June 2026 | 47
Cheltenham non-parish | 2.16 days | June 2026 | June 2026 | 54
Charlton Kings | 1.92 days | June 2026 | June 2026 | 48
Shurdington | 0.28 days | June 2026 | June 2026 | 7
Badgeworth | 0.16 days | June 2026 | June 2026 | 4
Brockworth | 0.56 days | June 2026 | June 2026 | 14
Churchdown | 0.12 days | June 2026 | June 2026 | 3
Hucclecote | 0.32 days | June 2026 | June 2026 | 8
South | 57.48 days | June 2026 | September 2026 | 1471
Gloucester non-parish | 1.68 days | June 2026 | June 2026 | 42
Quedgeley | 0.16 days | June 2026 | June 2026 | 4
Haresfield | 0.32 days | June 2026 | June 2026 | 8
Harescombe | 0.4 days | June 2026 | June 2026 | 10
Pitchcombe | 0.68 days | June 2026 | June 2026 | 17
Painswick | 6.32 days | June 2026 | July 2026 | 158
Cranham | 0.2 days | July 2026 | July 2026 | 5
Upton St. Leonards | 0.88 days | July 2026 | July 2026 | 22
Miserden | 0.16 days | July 2026 | July 2026 | 4
Bisley-with-Lypiatt | 4.28 days | July 2026 | July 2026 | 107
Chalford | 5.12 days | July 2026 | July 2026 | 128
Brimscombe and Thrupp | 4.48 days | July 2026 | July 2026 | 112
Minchinhampton | 6.76 days | July 2026 | August 2026 | 169
Nailsworth | 3.72 days | August 2026 | August 2026 | 93
Horsley | 1.52 days | August 2026 | August 2026 | 38
Nympsfield | 0.04 days | August 2026 | August 2026 | 1
Woodchester | 1.6 days | August 2026 | August 2026 | 40
Rodborough | 1.92 days | August 2026 | August 2026 | 48
Stroud | 1.32 days | August 2026 | August 2026 | 33
Whiteshill and Ruscombe | 0.84 days | August 2026 | August 2026 | 21
Randwick and Westrip | 1.36 days | August 2026 | August 2026 | 34
Cainscross | 0.52 days | August 2026 | August 2026 | 13
Stonehouse | 2.08 days | August 2026 | August 2026 | 52
Leonard Stanley | 0.08 days | August 2026 | August 2026 | 2
King's Stanley | 1.76 days | August 2026 | August 2026 | 44
Eastington | 0.6 days | August 2026 | August 2026 | 15
Standish | 0.36 days | August 2026 | August 2026 | 9
Frampton on Severn | 0.08 days | August 2026 | August 2026 | 2
Arlingham | 0.08 days | August 2026 | August 2026 | 2
Slimbridge | 0.68 days | August 2026 | August 2026 | 17
Coaley | 0.8 days | August 2026 | August 2026 | 20
Cam | 1.44 days | August 2026 | September 2026 | 36
Stinchcombe | 0.04 days | September 2026 | September 2026 | 1
Hamfallow | 0.04 days | September 2026 | September 2026 | 1
Berkeley | 0.04 days | September 2026 | September 2026 | 1
Ham and Stone | 0.04 days | September 2026 | September 2026 | 1
Stinchcombe | 0.04 days | September 2026 | September 2026 | 1
Dursley | 0.4 days | September 2026 | September 2026 | 10
North Nibley | 1.36 days | September 2026 | September 2026 | 34
Uley | 1.08 days | September 2026 | September 2026 | 27
Owlpen | 0.08 days | September 2026 | September 2026 | 2
Wotton-under-Edge | 2.2 days | September 2026 | September 2026 | 55
Kingswood | 0.64 days | September 2026 | September 2026 | 16
Hillesley and Tresham | 0.64 days | September 2026 | September 2026 | 16
East | 17.57 days | September 2026 | October 2026 | 466
Ozleworth | 0.2 days | September 2026 | September 2026 | 5
Kingscote | 0.44 days | September 2026 | September 2026 | 11
Tetbury Upton | 0.2 days | September 2026 | September 2026 | 5
Tetbury | 2.48 days | September 2026 | September 2026 | 62
Avening | 0.84 days | September 2026 | September 2026 | 21
Sapperton | 0.12 days | September 2026 | September 2026 | 3
Kemble | 0.04 days | September 2026 | September 2026 | 1
Siddington | 0.12 days | September 2026 | September 2026 | 3
South Cerney | 0.12 days | September 2026 | September 2026 | 3
Driffield | 0.04 days | September 2026 | September 2026 | 1
Cirencester | 4.24 days | September 2026 | September 2026 | 106
Bagendon | 0.44 days | September 2026 | September 2026 | 11
Duntisbourne Rouse | 0.08 days | September 2026 | September 2026 | 2
Edgeworth | 0.28 days | September 2026 | September 2026 | 7
Duntisbourne Abbots | 0.24 days | September 2026 | September 2026 | 6
North Cerney | 0.24 days | September 2026 | September 2026 | 6
Winstone | 1.04 days | September 2026 | September 2026 | 26
Elkstone | 0.12 days | September 2026 | September 2026 | 3
Syde | 0.52 days | September 2026 | September 2026 | 13
Brimpsfield | 1.09 days | September 2026 | September 2026 | 15
Cowley | 0.32 days | September 2026 | September 2026 | 8
Coberley | 0.16 days | September 2026 | September 2026 | 4
Dowdeswell | 0.12 days | September 2026 | September 2026 | 3
Withington | 0.2 days | September 2026 | September 2026 | 5
Chedworth | 1 day | September 2026 | September 2026 | 25
Northleach with Eastington | 0.44 days | September 2026 | September 2026 | 11
Farmington | 0.04 days | September 2026 | September 2026 | 1
Shipton | 0.04 days | September 2026 | September 2026 | 1
Sevenhampton | 0.04 days | September 2026 | September 2026 | 1
Guiting Power | 0.08 days | September 2026 | September 2026 | 2
Temple Guiting | 0.16 days | September 2026 | September 2026 | 4
Chipping Campden | 0.32 days | September 2026 | September 2026 | 8
Aston Subedge | 0.24 days | September 2026 | October 2026 | 6
Weston Subedge | 0.16 days | October 2026 | October 2026 | 4
Mickleton | 0.24 days | October 2026 | October 2026 | 6
Blockley | 0.16 days | October 2026 | October 2026 | 4
Moreton-in-Marsh | 0.84 days | October 2026 | October 2026 | 21
Stow-on-the-Wold | 0.28 days | October 2026 | October 2026 | 7
Maugersbury | 0.08 days | October 2026 | October 2026 | 2
Westcote | 0.24 days | October 2026 | October 2026 | 6
Lower Slaughter | 0.08 days | October 2026 | October 2026 | 2
Bourton-on-the-Water | 0.32 days | October 2026 | October 2026 | 8
Great Rissington | 0.16 days | October 2026 | October 2026 | 4
Barrington | 0.08 days | October 2026 | October 2026 | 2
Sherborne | 0.04 days | October 2026 | October 2026 | 1
Bibury | 0.12 days | October 2026 | October 2026 | 3
Winson | 0.12 days | October 2026 | October 2026 | 3
Maiseyhampton | 0.04 days | October 2026 | October 2026 | 1
Fairford | 0.12 days | October 2026 | October 2026 | 3