## Cyclical cleans
Name | Duration | Start Month | Finish Month
Standard Cleans | 246.84 days | April 2026 | March 2027
North | 195.31 days | April 2026 | January 2027
Prestbury Ward | 9.32 days | April 2026 | April 2026
Pittville Ward | 8.57 days | April 2026 | April 2026
Oakley Ward | 6.81 days | April 2026 | May 2026
Battledown Ward | 9.71 days | May 2026 | May 2026
Charlton Kings Ward | 7.62 days | May 2026 | June 2026
Charlton Park Ward | 7.04 days | June 2026 | June 2026
Leckhampton Ward | 9.71 days | June 2026 | July 2026
College Ward | 5.69 days | July 2026 | July 2026
All Saints Ward | 5.32 days | July 2026 | July 2026
St. Paul's Ward | 7.83 days | July 2026 | July 2026
St. Peter's Ward | 10.01 days | July 2026 | July 2026
Lansdown Ward | 5.47 days | July 2026 | August 2026
Park Ward | 9.69 days | August 2026 | August 2026
Warden Hill Ward | 11.26 days | August 2026 | September 2026
Up Hatherley Ward | 12.92 days | September 2026 | September 2026
Badgeworth Ward | 0.09 days | September 2026 | September 2026
Benhall and the Reddings Ward | 13.8 days | September 2026 | October 2026
St. Mark's Ward | 8.72 days | October 2026 | October 2026
Hesters Way Ward | 12.68 days | October 2026 | November 2026
Springbank Ward | 13.74 days | November 2026 | December 2026
Swindon Village Ward | 13.04 days | December 2026 | December 2026
Bishop's Cleeve | 29.54 days | April 2026 | May 2026
Minsterworth | 0.48 days | May 2026 | May 2026
Highnam | 5.29 days | May 2026 | May 2026
Maisemore | 0.73 days | May 2026 | May 2026
Longford | 3.23 days | May 2026 | May 2026
Sandhurst | 0.99 days | May 2026 | May 2026
Twigworth | 0.04 days | May 2026 | May 2026
Innsworth | 5.08 days | May 2026 | June 2026
Down Hatherley | 0.99 days | June 2026 | June 2026
Churchdown | 19.22 days | June 2026 | July 2026
Hucclecote | 7.3 days | July 2026 | July 2026
Brockworth | 14.33 days | July 2026 | July 2026
Great Witcombe | 0.38 days | July 2026 | July 2026
Badgeworth | 5.14 days | July 2026 | August 2026
Shurdington | 3.6 days | August 2026 | August 2026
Staverton | 0.76 days | August 2026 | August 2026
Boddington | 0.91 days | August 2026 | August 2026
Uckington | 1.7 days | August 2026 | August 2026
Elmstone Hardwicke | 0.41 days | August 2026 | August 2026
Leigh | 0.21 days | August 2026 | August 2026
Norton | 1.57 days | August 2026 | August 2026
Hasfield | 0.49 days | August 2026 | August 2026
Ashleworth | 1.76 days | August 2026 | August 2026
Tirley | 1.28 days | August 2026 | August 2026
Deerhurst | 1.43 days | August 2026 | August 2026
Chaceley | 0.21 days | August 2026 | August 2026
Forthampton | 0.18 days | August 2026 | August 2026
Tewkesbury | 24.59 days | August 2026 | October 2026
Twyning | 3.73 days | October 2026 | October 2026
Wheatpieces | 9.76 days | October 2026 | October 2026
Northway | 11.63 days | October 2026 | November 2026
Ashchurch Rural | 2.22 days | November 2026 | November 2026
Stoke Orchard | 3.57 days | November 2026 | November 2026
Gotherington | 2.89 days | November 2026 | November 2026
Prescott | 0.27 days | November 2026 | November 2026
Gretton | 1.47 days | November 2026 | November 2026
Alderton | 1.49 days | November 2026 | November 2026
Oxenton | 0.32 days | November 2026 | November 2026
Teddington | 0.91 days | November 2026 | November 2026
Dumbleton | 1.12 days | November 2026 | November 2026
Toddington | 0.78 days | November 2026 | November 2026
Stanton | 0.42 days | November 2026 | November 2026
Buckland | 0.48 days | November 2026 | November 2026
Snowshill | 0.42 days | November 2026 | November 2026
Stanway | 0.79 days | November 2026 | December 2026
Winchcombe | 9.83 days | December 2026 | December 2026
Sudeley | 0.57 days | December 2026 | December 2026
Hawling | 0.11 days | December 2026 | December 2026
Southam | 2.9 days | December 2026 | December 2026
Woodmancote | 7.79 days | December 2026 | December 2026
West | 152.95 days | April 2026 | October 2026
Tidenham | 9.31 days | April 2026 | April 2026
Hewelsfield and Brockweir | 0.62 days | April 2026 | April 2026
Woolaston | 2.69 days | April 2026 | April 2026
Alvington | 1 day | April 2026 | April 2026
Aylburton | 1.39 days | April 2026 | April 2026
St. Briavels | 2.99 days | April 2026 | April 2026
Newland | 2.41 days | April 2026 | April 2026
Coleford | 15.36 days | April 2026 | May 2026
Staunton Coleford | 0.66 days | May 2026 | May 2026
English Bicknor | 1.24 days | May 2026 | May 2026
Lydbrook | 3.21 days | May 2026 | May 2026
Ruardean | 3.24 days | May 2026 | June 2026
Drybrook | 5.19 days | June 2026 | June 2026
Cinderford | 15.89 days | June 2026 | July 2026
Ruspidge and Soudley | 5.84 days | July 2026 | July 2026
West Dean | 18.3 days | July 2026 | August 2026
Lydney | 18.52 days | August 2026 | August 2026
Awre | 4.74 days | August 2026 | August 2026
Newnham | 2.2 days | August 2026 | September 2026
Littledean | 1.93 days | September 2026 | September 2026
Westbury-on-Severn | 2.69 days | September 2026 | September 2026
Blaisdon | 1.03 days | September 2026 | September 2026
Mitcheldean | 3.86 days | September 2026 | September 2026
Longhope | 3.2 days | September 2026 | September 2026
Huntley | 1.96 days | September 2026 | September 2026
Churcham | 0.81 days | September 2026 | September 2026
Tibberton | 1.1 days | September 2026 | October 2026
Taynton | 0.63 days | October 2026 | October 2026
Newent | 12.18 days | October 2026 | October 2026
Gorsley and Kilcot | 0.22 days | October 2026 | October 2026
Oxenhall | 0.24 days | October 2026 | October 2026
Kempley | 0.26 days | October 2026 | October 2026
Dymock | 1.62 days | October 2026 | October 2026
Bromesberrow | 0.52 days | October 2026 | October 2026
Redmarley D'abitot | 1.03 days | October 2026 | October 2026
Pauntley | 0.31 days | October 2026 | October 2026
Upleadon | 0.4 days | October 2026 | October 2026
Staunton | 1.77 days | October 2026 | October 2026
Corse | 0.7 days | October 2026 | October 2026
Hartpury | 1.39 days | October 2026 | October 2026
Rudford and Highleadon | 0.3 days | October 2026 | October 2026
South | 246.84 days | April 2026 | March 2027
Quedgeley Fieldcourt Ward | 37.6 days | April 2026 | May 2026
Quedgeley Severn Vale Ward | 19.97 days | May 2026 | June 2026
Grange Ward | 11.94 days | June 2026 | July 2026
Tuffley Ward | 10.26 days | July 2026 | July 2026
Matson and Robinswood Ward | 17.53 days | July 2026 | August 2026
Moreland Ward | 9.98 days | August 2026 | August 2026
Podsmead Ward | 8.92 days | August 2026 | September 2026
Westgate Ward | 17.99 days | September 2026 | October 2026
Barton and Tredworth Ward | 11.4 days | October 2026 | October 2026
Abbey Ward | 18.61 days | October 2026 | November 2026
Hucclecote Ward | 18.76 days | November 2026 | December 2026
Barnwood Ward | 26.06 days | December 2026 | January 2027
Elmbridge Ward | 8.27 days | January 2027 | January 2027
Longlevens Ward | 20.08 days | January 2027 | February 2027
Kingsholm and Wotton Ward | 9.47 days | February 2027 | March 2027
Whitminster | 2.68 days | April 2026 | April 2026
Moreton Valence | 0.5 days | April 2026 | April 2026
Standish | 0.61 days | April 2026 | April 2026
Haresfield | 2.17 days | April 2026 | April 2026
Hardwicke | 13.67 days | April 2026 | April 2026
Elmore | 0.59 days | April 2026 | April 2026
Longney and Epney | 0.67 days | April 2026 | April 2026
Fretherne with Saul | 0.8 days | April 2026 | April 2026
Arlingham | 1.26 days | April 2026 | May 2026
Frampton on Severn | 2.03 days | May 2026 | May 2026
Slimbridge | 2.91 days | May 2026 | May 2026
Coaley | 1.89 days | May 2026 | May 2026
Cam | 14.61 days | May 2026 | June 2026
Stinchcombe | 0.78 days | June 2026 | June 2026
Hamfallow | 1.9 days | June 2026 | June 2026
Hinton | 1.99 days | June 2026 | June 2026
Berkeley | 3.87 days | June 2026 | June 2026
Ham and Stone | 1.77 days | June 2026 | June 2026
Alkington | 1.26 days | June 2026 | June 2026
North Nibley | 1.11 days | June 2026 | June 2026
Dursley | 11.36 days | June 2026 | July 2026
Uley | 1.47 days | July 2026 | July 2026
Owlpen | 0.04 days | July 2026 | July 2026
Wotton-under-Edge | 6.67 days | July 2026 | July 2026
Kingswood | 2.53 days | July 2026 | July 2026
Hillesley and Tresham | 0.94 days | July 2026 | July 2026
Alderley | 0.36 days | July 2026 | July 2026
Horsley | 0.67 days | July 2026 | July 2026
Nympsfield | 0.62 days | July 2026 | July 2026
Frocester | 0.59 days | July 2026 | July 2026
Leonard Stanley | 3.69 days | July 2026 | July 2026
King's Stanley | 3.99 days | July 2026 | August 2026
Woodchester | 1.98 days | August 2026 | August 2026
Nailsworth | 8.1 days | August 2026 | August 2026
Minchinhampton | 8.39 days | August 2026 | August 2026
Rodborough | 6.07 days | August 2026 | September 2026
Brimscombe and Thrupp | 2.13 days | September 2026 | September 2026
Chalford | 10.6 days | September 2026 | September 2026
Bisley-with-Lypiatt | 3.73 days | September 2026 | September 2026
Stroud | 17.83 days | October 2026 | October 2026
Cainscross | 9.64 days | October 2026 | November 2026
Stonehouse | 14.57 days | November 2026 | November 2026
Eastington | 5.29 days | November 2026 | December 2026
Randwick | 2.19 days | December 2026 | December 2026
Whiteshill and Ruscombe | 1.23 days | December 2026 | December 2026
Pitchcombe | 0.27 days | December 2026 | December 2026
Harescombe | 0.73 days | December 2026 | December 2026
Painswick | 3.44 days | December 2026 | December 2026
Miserden | 0.4 days | December 2026 | December 2026
Cranham | 0.48 days | December 2026 | December 2026
Upton St. Leonards | 5.26 days | December 2026 | December 2026
Brookthorpe-with-Whaddon | 0.91 days | December 2026 | December 2026
East | 172.85 days | April 2026 | November 2026
Ebrington | 1.22 days | April 2026 | April 2026
Mickleton | 3.93 days | April 2026 | April 2026
Weston Subedge | 1.02 days | April 2026 | April 2026
Aston Subedge | 0.17 days | April 2026 | April 2026
Saintbury | 0.1 days | April 2026 | April 2026
Willersey | 1.93 days | April 2026 | April 2026
Chipping Campden | 4.3 days | April 2026 | April 2026
Blockley | 3.17 days | April 2026 | April 2026
Batsford | 0.47 days | April 2026 | April 2026
Todenham | 0.52 days | April 2026 | April 2026
Moreton-in-Marsh | 9.11 days | April 2026 | May 2026
Bourton-on-the-Hill | 0.18 days | May 2026 | May 2026
Cutsdean | 0.01 days | May 2026 | May 2026
Temple Guiting | 0.49 days | May 2026 | May 2026
Swell | 0.37 days | May 2026 | May 2026
Condicote | 0.14 days | May 2026 | May 2026
Longborough | 0.8 days | May 2026 | May 2026
Donnington | 0.07 days | May 2026 | May 2026
Evenlode | 0.24 days | May 2026 | May 2026
Adlestrop | 0.22 days | May 2026 | May 2026
Oddington | 0.66 days | May 2026 | May 2026
Bledington | 0.64 days | May 2026 | May 2026
Maugersbury | 0.27 days | May 2026 | May 2026
Broadwell | 0.67 days | May 2026 | May 2026
Stow-on-the-Wold | 2.69 days | May 2026 | May 2026
Upper Slaughter | 0.3 days | May 2026 | May 2026
Naunton | 0.48 days | May 2026 | May 2026
Guiting Power | 0.43 days | May 2026 | May 2026
Sevenhampton | 0.21 days | May 2026 | May 2026
Whittington | 0.31 days | May 2026 | May 2026
Andoversford | 2.01 days | May 2026 | May 2026
Shipton | 0.32 days | May 2026 | May 2026
Compton Abdale | 0.4 days | May 2026 | May 2026
Hazleton | 0.29 days | May 2026 | May 2026
Turkdean | 0.06 days | May 2026 | May 2026
Notgrove | 0.08 days | May 2026 | May 2026
Cold Aston | 0.33 days | May 2026 | May 2026
Bourton-on-the-Water | 10.36 days | May 2026 | June 2026
Lower Slaughter | 0.67 days | June 2026 | June 2026
Wick Rissington | 0.38 days | June 2026 | June 2026
Icomb | 0.28 days | June 2026 | June 2026
Westcote | 0.29 days | June 2026 | June 2026
Upper Rissington | 2.37 days | June 2026 | June 2026
Little Rissington | 1.13 days | June 2026 | June 2026
Clapton | 0.22 days | June 2026 | June 2026
Farmington | 0.48 days | June 2026 | June 2026
Sherborne | 0.57 days | June 2026 | June 2026
Great Rissington | 0.64 days | June 2026 | June 2026
Barrington | 0.62 days | June 2026 | June 2026
Windrush | 0.14 days | June 2026 | June 2026
Aldsworth | 0.29 days | June 2026 | June 2026
Northleach with Eastington | 4.32 days | June 2026 | June 2026
Hampnett | 0.21 days | June 2026 | June 2026
Yanworth | 0.1 days | June 2026 | June 2026
Chedworth | 1.06 days | June 2026 | June 2026
Withington | 1.02 days | June 2026 | June 2026
Colesbourne | 0.09 days | June 2026 | June 2026
Dowdeswell | 0.42 days | June 2026 | June 2026
Coberley | 0.72 days | June 2026 | June 2026
Cowley | 1.28 days | June 2026 | July 2026
Brimpsfield | 0.3 days | July 2026 | July 2026
Syde | 0.57 days | July 2026 | July 2026
Elkstone | 0.66 days | July 2026 | July 2026
Rendcomb | 0.54 days | July 2026 | July 2026
North Cerney | 0.76 days | July 2026 | July 2026
Coln St. Dennis | 0.38 days | July 2026 | July 2026
Winson | 0.16 days | July 2026 | July 2026
Bibury | 0.8 days | July 2026 | July 2026
Coln St. Aldwyns | 0.39 days | July 2026 | July 2026
Eastleach | 0.27 days | July 2026 | July 2026
Hatherop | 0.38 days | July 2026 | July 2026
Southrop | 0.73 days | July 2026 | July 2026
Lechlade | 5.3 days | July 2026 | July 2026
Kempsford | 4.54 days | July 2026 | July 2026
Fairford | 7.43 days | July 2026 | August 2026
Quenington | 0.71 days | August 2026 | August 2026
Maiseyhampton | 0.88 days | August 2026 | August 2026
Poulton | 0.76 days | August 2026 | August 2026
Down Ampney | 1.54 days | August 2026 | August 2026
Ampney St. Peter | 0.08 days | August 2026 | August 2026
Ampney St. Mary | 0.38 days | August 2026 | August 2026
Ampney Crucis | 1.61 days | August 2026 | August 2026
Barnsley | 0.02 days | August 2026 | August 2026
Preston | 2.96 days | August 2026 | August 2026
Driffield | 0.99 days | August 2026 | August 2026
South Cerney | 8.84 days | August 2026 | August 2026
Siddington | 3.33 days | August 2026 | September 2026
Cirencester | 38.07 days | September 2026 | October 2026
Baunton | 0.6 days | October 2026 | October 2026
Bagendon | 0.56 days | October 2026 | October 2026
Daglingworth | 0.8 days | October 2026 | October 2026
Duntisbourne Rouse | 0.23 days | October 2026 | October 2026
Duntisbourne Abbots | 1.31 days | October 2026 | November 2026
Winstone | 0.77 days | November 2026 | November 2026
Edgeworth | 0.2 days | November 2026 | November 2026
Sapperton | 0.91 days | November 2026 | November 2026
Coates | 0.58 days | November 2026 | November 2026
Kemble | 1.82 days | November 2026 | November 2026
Somerford Keynes | 1.11 days | November 2026 | November 2026
Poole Keynes | 0.66 days | November 2026 | November 2026
Rodmarton | 0.43 days | November 2026 | November 2026
Cherington | 0.12 days | November 2026 | November 2026
Ashley | 0.27 days | November 2026 | November 2026
Long Newnton | 0.07 days | November 2026 | November 2026
Shipton Moyne | 0.4 days | November 2026 | November 2026
Tetbury Upton | 0.61 days | November 2026 | November 2026
Tetbury | 8.47 days | November 2026 | November 2026
Avening | 1.38 days | November 2026 | November 2026
Beverston | 0.16 days | November 2026 | November 2026
Kingscote | 0.43 days | November 2026 | November 2026
Ozleworth | 0.07 days | November 2026 | November 2026
Boxwell with Leighterton | 0.32 days | November 2026 | November 2026
Westonbirt with Lasborough | 0.54 days | November 2026 | November 2026
Didmarton | 0.38 days | November 2026 | November 2026

## A&B roads
Name | Duration | Number of Gullies | Start Month | Finish Month
A&B Roads | 215.62 days | 25762 | April 2026 | January 2027
North | 76.53 days | 6886 | October 2026 | January 2027
A38 | 15.18 days | 1366 | October 2026 | October 2026
A40 | 6.07 days | 546 | October 2026 | October 2026
A4013 | 1.51 days | 136 | October 2026 | October 2026
A4015 | 0.19 days | 17 | October 2026 | November 2026
A4019 | 6.39 days | 575 | November 2026 | November 2026
A417 | 2.69 days | 242 | November 2026 | November 2026
A435 | 8.01 days | 721 | November 2026 | November 2026
A436 | 0.62 days | 56 | November 2026 | November 2026
A438 | 1.8 days | 162 | November 2026 | November 2026
A46 | 9.17 days | 825 | November 2026 | November 2026
A48 | 2.86 days | 257 | November 2026 | December 2026
B4063 | 3.14 days | 283 | December 2026 | December 2026
B4068 | 0.28 days | 25 | December 2026 | December 2026
B4075 | 2.06 days | 185 | December 2026 | December 2026
B4077 | 1.86 days | 167 | December 2026 | December 2026
B4078 | 1.49 days | 134 | December 2026 | December 2026
B4079 | 0.59 days | 53 | December 2026 | December 2026
B4080 | 0.43 days | 39 | December 2026 | December 2026
B4213 | 1.67 days | 150 | December 2026 | December 2026
B4215 | 0.6 days | 54 | December 2026 | January 2027
B4632 | 6.6 days | 594 | January 2027 | January 2027
B4633 | 0.71 days | 64 | January 2027 | January 2027
B4634 | 1.73 days | 156 | January 2027 | January 2027
B4641 | 0.88 days | 79 | January 2027 | January 2027
West | 60.87 days | 5482 | April 2026 | June 2026
A4136 | 6.73 days | 606 | April 2026 | April 2026
A40 | 0.02 days | 2 | April 2026 | April 2026
A4151 | 2.94 days | 265 | April 2026 | April 2026
A417 | 2.51 days | 226 | April 2026 | April 2026
A4172 | 0.33 days | 30 | April 2026 | April 2026
A466 | 2.41 days | 217 | April 2026 | April 2026
A48 | 17.94 days | 1615 | April 2026 | April 2026
B4024 | 0.01 days | 1 | April 2026 | May 2026
B4028 | 0.63 days | 57 | May 2026 | May 2026
B4208 | 0.16 days | 14 | May 2026 | May 2026
B4211 | 0.04 days | 4 | May 2026 | May 2026
B4213 | 0.12 days | 11 | May 2026 | May 2026
A449 | 0.01 days | 1 | May 2026 | May 2026
B4215 | 5.46 days | 491 | May 2026 | May 2026
B4216 | 1.77 days | 159 | May 2026 | May 2026
B4221 | 0.9 days | 81 | May 2026 | May 2026
B4222 | 0.01 days | 1 | May 2026 | May 2026
B4224 | 0.78 days | 70 | May 2026 | May 2026
B4226 | 2.09 days | 188 | May 2026 | May 2026
B4227 | 2.28 days | 205 | May 2026 | June 2026
B4228 | 5.18 days | 466 | June 2026 | June 2026
B4231 | 2.73 days | 246 | June 2026 | June 2026
B4234 | 5.27 days | 474 | June 2026 | June 2026
B4432 | 0.58 days | 52 | June 2026 | June 2026
South | 84.62 days | 7615 | October 2026 | January 2027
A38 | 18.68 days | 1681 | October 2026 | October 2026
A40 | 0.71 days | 64 | October 2026 | October 2026
A4135 | 3 days | 270 | October 2026 | October 2026
A417 | 3.77 days | 339 | October 2026 | November 2026
A4171 | 1.32 days | 119 | November 2026 | November 2026
A4173 | 3.47 days | 312 | November 2026 | November 2026
A419 | 10.79 days | 971 | November 2026 | November 2026
A430 | 4.97 days | 447 | November 2026 | November 2026
A4301 | 1.03 days | 93 | November 2026 | December 2026
A4302 | 0.98 days | 88 | December 2026 | December 2026
A46 | 8.37 days | 753 | December 2026 | December 2026
B4008 | 8.36 days | 752 | December 2026 | December 2026
B4014 | 0.57 days | 51 | December 2026 | December 2026
B4058 | 2.17 days | 195 | December 2026 | January 2027
B4060 | 1.51 days | 136 | January 2027 | January 2027
B4062 | 0.54 days | 49 | January 2027 | January 2027
B4063 | 2.34 days | 211 | January 2027 | January 2027
B4066 | 4.29 days | 386 | January 2027 | January 2027
B4070 | 1.01 days | 91 | January 2027 | January 2027
B4071 | 1.44 days | 130 | January 2027 | January 2027
B4072 | 2.13 days | 192 | January 2027 | January 2027
B4073 | 3.17 days | 285 | January 2027 | January 2027
East | 64.2 days | 5779 | April 2026 | June 2026
A361 | 1.71 days | 154 | April 2026 | April 2026
A40 | 11.31 days | 1018 | April 2026 | April 2026
A4135 | 0.62 days | 56 | April 2026 | April 2026
A417 | 6.33 days | 570 | April 2026 | April 2026
A419 | 4.17 days | 375 | April 2026 | April 2026
A424 | 0.72 days | 65 | April 2026 | May 2026
A429 | 12.08 days | 1087 | May 2026 | May 2026
A433 | 3.86 days | 347 | May 2026 | May 2026
A435 | 5.01 days | 451 | May 2026 | May 2026
A436 | 1.73 days | 156 | May 2026 | June 2026
A44 | 2.24 days | 202 | June 2026 | June 2026
A46 | 1.68 days | 151 | June 2026 | June 2026
B4014 | 1.87 days | 168 | June 2026 | June 2026
B4035 | 1.08 days | 97 | June 2026 | June 2026
B4058 | 0.07 days | 6 | June 2026 | June 2026
B4068 | 0.83 days | 75 | June 2026 | June 2026
B4070 | 0.63 days | 57 | June 2026 | June 2026
B4077 | 0.63 days | 57 | June 2026 | June 2026
B4081 | 1.14 days | 103 | June 2026 | June 2026
B4425 | 2.42 days | 218 | April 2026 | April 2026
B4450 | 0.43 days | 39 | April 2026 | April 2026
B4479 | 1.18 days | 106 | April 2026 | April 2026
B4632 | 2.29 days | 206 | April 2026 | April 2026
B4696 | 0.17 days | 15 | April 2026 | April 2026

## Multicleans
Name | Duration | Start Month | Finish Month
Multicleans | 20.17 days
North | 8.13 days | April 2026 | April 20262
Badgeworth | 0.21 days | April 2026 | April 2026
Cheltenham non-parish | 0.29 days | April 2026 | April 2026
Charlton Kings | 0.16 days | April 2026 | April 2026
Boddington | 0.3 days | April 2026 | April 2026
Churchdown | 0.28 days | April 2026 | April 2026
Twigworth | 0.04 days | April 2026 | April 2026
Longford | 0.34 days | April 2026 | April 2026
Maisemore | 0.01 days | April 2026 | April 2026
Sandhurst | 0.45 days | April 2026 | April 2026
Ashleworth | 0.39 days | April 2026 | April 2026
Norton | 0.08 days | April 2026 | April 2026
Deerhurst | 0.01 days | April 2026 | April 2026
Chaceley | 0.16 days | April 2026 | April 2026
Tewkesbury | 0.63 days | April 2026 | April 2026
Twyning | 0.68 days | April 2026 | April 2026
Ashchurch Rural | 0.62 days | April 2026 | April 2026
Teddington | 0.09 days | April 2026 | April 2026
Bishop's Cleeve | 2.16 days | April 2026 | April 2026
Southam | 0.24 days | April 2026 | April 2026
Sudeley | 0.15 days | April 2026 | April 2026
Winchcombe | 0.55 days | April 2026 | April 2026
Gretton | 0.29 days | April 2026 | April 2026
West | 7.69 days | April 2026 | April 20262
Bromesberrow | 0.08 days | April 2026 | April 2026
Redmarley d'Abitot | 0.16 days | April 2026 | April 2026
Newent | 0.24 days | April 2026 | April 2026
Oxenhall | 0.17 days | April 2026 | April 2026
Rudford and Highleadon | 0.2 days | April 2026 | April 2026
Tibberton | 0.02 days | April 2026 | April 2026
Churcham | 0.01 days | April 2026 | April 2026
Westbury-on-Severn | 0.65 days | April 2026 | April 2026
Blaisdon | 0.38 days | April 2026 | April 2026
Newnham | 0.31 days | April 2026 | April 2026
Ruspidge and Soudley | 0.28 days | April 2026 | April 2026
Littledean | 0.58 days | April 2026 | April 2026
Cinderford | 0.54 days | April 2026 | April 2026
Longhope | 0.72 days | April 2026 | April 2026
Drybrook | 0.34 days | April 2026 | April 2026
Lydbrook | 0.03 days | April 2026 | April 2026
English Bicknor | 0.02 days | April 2026 | April 2026
Coleford | 0.51 days | April 2026 | April 2026
Newland | 0.41 days | April 2026 | April 2026
West Dean | 0.51 days | April 2026 | April 2026
Awre | 0.22 days | April 2026 | April 2026
Lydney | 1.1 days | April 2026 | April 2026
Alvington | 0.21 days | April 2026 | April 2026
South | 10.68 days | April 2026 | April 20262
Whitminster | 0.01 days | April 2026 | April 2026
Moreton Valence | 0.1 days | April 2026 | April 2026
Elmore | 0.03 days | April 2026 | April 2026
Longney and Epney | 0.3 days | April 2026 | April 2026
Fretherne with Saul | 0.48 days | April 2026 | April 2026
Arlingham | 0.23 days | April 2026 | April 2026
Frampton on Severn | 0.52 days | April 2026 | April 2026
Slimbridge | 0.93 days | April 2026 | April 2026
Hamfallow | 0.08 days | April 2026 | April 2026
Berkeley | 0.12 days | April 2026 | April 2026
Ham and Stone | 0.08 days | April 2026 | April 2026
Alkington | 0.17 days | April 2026 | April 2026
Cam | 0.37 days | April 2026 | April 2026
Dursley | 0.08 days | April 2026 | April 2026
Uley | 0.12 days | April 2026 | April 2026
Wotton-under-Edge | 0.31 days | April 2026 | April 2026
Nailsworth | 0.96 days | April 2026 | April 2026
Minchinhampton | 0.08 days | April 2026 | April 2026
Woodchester | 0.24 days | April 2026 | April 2026
Rodborough | 0.14 days | April 2026 | April 2026
Brimscombe and Thrupp | 0.59 days | April 2026 | April 2026
Chalford | 0.69 days | April 2026 | April 2026
Bisley-with-Lypiatt | 0.4 days | April 2026 | April 2026
Cranham | 0.49 days | April 2026 | April 2026
Upton St. Leonards | 0.45 days | April 2026 | April 2026
Painswick | 0.27 days | April 2026 | April 2026
Stroud | 0.41 days | April 2026 | April 2026
Cainscross | 0.19 days | April 2026 | April 2026
King's Stanley | 0.12 days | April 2026 | April 2026
Leonard Stanley | 0.57 days | April 2026 | April 2026
Stonehouse | 0.86 days | April 2026 | April 2026
Haresfield | 0.29 days | April 2026 | April 2026
East | 20.17 days | April 2026 | April 20262
Weston Subedge | 0.31 days | April 2026 | April 2026
Coberley | 0.02 days | April 2026 | April 2026
Cowley | 0.01 days | April 2026 | April 2026
Chipping Campden | 0.52 days | April 2026 | April 2026
Blockley | 0.11 days | April 2026 | April 2026
Moreton-in-Marsh | 0.39 days | April 2026 | April 2026
Evenlode | 0.01 days | April 2026 | April 2026
Condicote | 0.01 days | April 2026 | April 2026
Swell | 0.03 days | April 2026 | April 2026
Bledington | 0.08 days | April 2026 | April 2026
Lower Slaughter | 0.34 days | April 2026 | April 2026
Upper Slaughter | 0.08 days | April 2026 | April 2026
Naunton | 0.24 days | April 2026 | April 2026
Whittington | 0.1 days | April 2026 | April 2026
Andoversford | 0.72 days | April 2026 | April 2026
Chedworth | 0.21 days | April 2026 | April 2026
Coln St. Dennis | 0.13 days | April 2026 | April 2026
Barrington | 0.72 days | April 2026 | April 2026
Windrush | 0.68 days | April 2026 | April 2026
Sherborne | 1.2 days | April 2026 | April 2026
Farmington | 0.72 days | April 2026 | April 2026
Northleach with Eastington | 1 day | April 2026 | April 2026
Hampnett | 2.03 days | April 2026 | April 2026
Hazleton | 0.44 days | April 2026 | April 2026
Compton Abdale | 0.37 days | April 2026 | April 2026
Shipton | 1.71 days | April 2026 | April 2026
Dowdeswell | 0.65 days | April 2026 | April 2026
Elkstone | 0.4 days | April 2026 | April 2026
Syde | 0.41 days | April 2026 | April 2026
Colesbourne | 0.09 days | April 2026 | April 2026
Daglingworth | 0.02 days | April 2026 | April 2026
Cirencester | 3.1 days | April 2026 | April 2026
Siddington | 0.2 days | April 2026 | April 2026
Ampney St. Mary | 0.1 days | April 2026 | April 2026
Bibury | 0.1 days | April 2026 | April 2026
Fairford | 0.04 days | April 2026 | April 2026
South Cerney | 1.71 days | April 2026 | April 2026
Somerford Keynes | 0.02 days | April 2026 | April 2026
Avening | 0.04 days | April 2026 | April 2026
Tetbury Upton | 0.03 days | April 2026 | April 2026
Tetbury | 0.57 days | April 2026 | April 2026
Long Newnton | 0.03 days | April 2026 | April 2026
Shipton Moyne | 0.3 days | April 2026 | April 2026
Westonbirt with Lasborough | 0.18 days | April 2026 | April 2026

## Small unit
Name | Duration | Start Month | Finish Month
Small Units | 132.57 days
West | 46.8 days | April 2026 | June 2026
Tidenham | 1.36 days | April 2026 | April 2026
Woolaston | 1.92 days | April 2026 | April 2026
Hewelsfield and Brockweir | 1.36 days | April 2026 | April 2026
St. Briavels | 3.8 days | April 2026 | April 2026
Alvington | 0.24 days | April 2026 | April 2026
Aylburton | 0.56 days | April 2026 | April 2026
Lydney | 0.48 days | April 2026 | April 2026
Awre | 7.2 days | April 2026 | April 2026
West Dean | 4.76 days | April 2026 | April 2026
Newland | 0.4 days | April 2026 | May 2026
Coleford | 1.12 days | May 2026 | May 2026
Staunton Coleford | 0.8 days | May 2026 | May 2026
English Bicknor | 0.52 days | May 2026 | May 2026
Lydbrook | 3.96 days | May 2026 | May 2026
Ruardean | 0.88 days | May 2026 | May 2026
Drybrook | 1.16 days | May 2026 | May 2026
Cinderford | 2.2 days | May 2026 | May 2026
Ruspidge and Soudley | 1.84 days | May 2026 | May 2026
Newnham | 4 days | May 2026 | May 2026
Littledean | 1.64 days | May 2026 | May 2026
Mitcheldean | 1.08 days | May 2026 | May 2026
Longhope | 2.68 days | May 2026 | June 2026
Blaisdon | 0.72 days | June 2026 | June 2026
Westbury-on-Severn | 1.6 days | June 2026 | June 2026
Taynton | 0.64 days | June 2026 | June 2026
Newent | 1.36 days | June 2026 | June 2026
Gorsley and Kilcot | 0.04 days | June 2026 | June 2026
Oxenhall | 0.04 days | June 2026 | June 2026
Dymock | 0.04 days | June 2026 | June 2026
Pauntley | 0.12 days | June 2026 | June 2026
Redmarley D'Abitot | 0.28 days | June 2026 | June 2026
Bromesberrow | 0.52 days | June 2026 | June 2026
North | 83.33 days | June 2026 | June 20262
Maisemore | 0.04 days | June 2026 | June 2026
Leigh | 0.4 days | June 2026 | June 2026
Deerhurst | 0.16 days | June 2026 | June 2026
Tewkesbury | 0.84 days | June 2026 | June 2026
Twyning | 0.64 days | June 2026 | June 2026
Ashchurch Rural | 0.16 days | June 2026 | June 2026
Stanton | 0.16 days | June 2026 | June 2026
Toddington | 0.2 days | June 2026 | June 2026
Gretton | 0.24 days | June 2026 | June 2026
Prescott | 0.2 days | June 2026 | June 2026
Winchcombe | 1.04 days | June 2026 | June 2026
Hawling | 0.08 days | June 2026 | June 2026
Southam | 0.32 days | June 2026 | June 2026
Woodmancote | 1.88 days | June 2026 | June 2026
Cheltenham non-parish | 2.16 days | June 2026 | June 2026
Charlton Kings | 1.92 days | June 2026 | June 2026
Shurdington | 0.28 days | June 2026 | June 2026
Badgeworth | 0.16 days | June 2026 | June 2026
Brockworth | 0.56 days | June 2026 | June 2026
Churchdown | 0.12 days | June 2026 | June 2026
Hucclecote | 0.32 days | June 2026 | June 2026
South | 57.48 days | June 2026 | September 2026
Gloucester non-parish | 1.68 days | June 2026 | June 2026
Quedgeley | 0.16 days | June 2026 | June 2026
Haresfield | 0.32 days | June 2026 | June 2026
Harescombe | 0.4 days | June 2026 | June 2026
Pitchcombe | 0.68 days | June 2026 | June 2026
Painswick | 6.32 days | June 2026 | July 2026
Cranham | 0.2 days | July 2026 | July 2026
Upton St. Leonards | 0.88 days | July 2026 | July 2026
Miserden | 0.16 days | July 2026 | July 2026
Bisley-with-Lypiatt | 4.28 days | July 2026 | July 2026
Chalford | 5.12 days | July 2026 | July 2026
Brimscombe and Thrupp | 4.48 days | July 2026 | July 2026
Minchinhampton | 6.76 days | July 2026 | August 2026
Nailsworth | 3.72 days | August 2026 | August 2026
Horsley | 1.52 days | August 2026 | August 2026
Nympsfield | 0.04 days | August 2026 | August 2026
Woodchester | 1.6 days | August 2026 | August 2026
Rodborough | 1.92 days | August 2026 | August 2026
Stroud | 1.32 days | August 2026 | August 2026
Whiteshill and Ruscombe | 0.84 days | August 2026 | August 2026
Randwick and Westrip | 1.36 days | August 2026 | August 2026
Cainscross | 0.52 days | August 2026 | August 2026
Stonehouse | 2.08 days | August 2026 | August 2026
Leonard Stanley | 0.08 days | August 2026 | August 2026
King's Stanley | 1.76 days | August 2026 | August 2026
Eastington | 0.6 days | August 2026 | August 2026
Standish | 0.36 days | August 2026 | August 2026
Frampton on Severn | 0.08 days | August 2026 | August 2026
Arlingham | 0.08 days | August 2026 | August 2026
Slimbridge | 0.68 days | August 2026 | August 2026
Coaley | 0.8 days | August 2026 | August 2026
Cam | 1.44 days | August 2026 | September 2026
Stinchcombe | 0.04 days | September 2026 | September 2026
Hamfallow | 0.04 days | September 2026 | September 2026
Berkeley | 0.04 days | September 2026 | September 2026
Ham and Stone | 0.04 days | September 2026 | September 2026
Stinchcombe | 0.04 days | September 2026 | September 2026
Dursley | 0.4 days | September 2026 | September 2026
North Nibley | 1.36 days | September 2026 | September 2026
Uley | 1.08 days | September 2026 | September 2026
Owlpen | 0.08 days | September 2026 | September 2026
Wotton-under-Edge | 2.2 days | September 2026 | September 2026
Kingswood | 0.64 days | September 2026 | September 2026
Hillesley and Tresham | 0.64 days | September 2026 | September 2026
East | 17.57 days | September 2026 | October 2026
Ozleworth | 0.2 days | September 2026 | September 2026
Kingscote | 0.44 days | September 2026 | September 2026
Tetbury Upton | 0.2 days | September 2026 | September 2026
Tetbury | 2.48 days | September 2026 | September 2026
Avening | 0.84 days | September 2026 | September 2026
Sapperton | 0.12 days | September 2026 | September 2026
Kemble | 0.04 days | September 2026 | September 2026
Siddington | 0.12 days | September 2026 | September 2026
South Cerney | 0.12 days | September 2026 | September 2026
Driffield | 0.04 days | September 2026 | September 2026
Cirencester | 4.24 days | September 2026 | September 2026
Bagendon | 0.44 days | September 2026 | September 2026
Duntisbourne Rouse | 0.08 days | September 2026 | September 2026
Edgeworth | 0.28 days | September 2026 | September 2026
Duntisbourne Abbots | 0.24 days | September 2026 | September 2026
North Cerney | 0.24 days | September 2026 | September 2026
Winstone | 1.04 days | September 2026 | September 2026
Elkstone | 0.12 days | September 2026 | September 2026
Syde | 0.52 days | September 2026 | September 2026
Brimpsfield | 1.09 days | September 2026 | September 2026
Cowley | 0.32 days | September 2026 | September 2026
Coberley | 0.16 days | September 2026 | September 2026
Dowdeswell | 0.12 days | September 2026 | September 2026
Withington | 0.2 days | September 2026 | September 2026
Chedworth | 1 day | September 2026 | September 2026
Northleach with Eastington | 0.44 days | September 2026 | September 2026
Farmington | 0.04 days | September 2026 | September 2026
Shipton | 0.04 days | September 2026 | September 2026
Sevenhampton | 0.04 days | September 2026 | September 2026
Guiting Power | 0.08 days | September 2026 | September 2026
Temple Guiting | 0.16 days | September 2026 | September 2026
Chipping Campden | 0.32 days | September 2026 | September 2026
Aston Subedge | 0.24 days | September 2026 | October 2026
Weston Subedge | 0.16 days | October 2026 | October 2026
Mickleton | 0.24 days | October 2026 | October 2026
Blockley | 0.16 days | October 2026 | October 2026
Moreton-in-Marsh | 0.84 days | October 2026 | October 2026
Stow-on-the-Wold | 0.28 days | October 2026 | October 2026
Maugersbury | 0.08 days | October 2026 | October 2026
Westcote | 0.24 days | October 2026 | October 2026
Lower Slaughter | 0.08 days | October 2026 | October 2026
Bourton-on-the-Water | 0.32 days | October 2026 | October 2026
Great Rissington | 0.16 days | October 2026 | October 2026
Barrington | 0.08 days | October 2026 | October 2026
Sherborne | 0.04 days | October 2026 | October 2026
Bibury | 0.12 days | October 2026 | October 2026
Winson | 0.12 days | October 2026 | October 2026
Maiseyhampton | 0.04 days | October 2026 | October 2026
Fairford | 0.12 days | October 2026 | October 2026